## Project Tracking
Sprint # | Sprint Name | Task ID | Task Title | User Story (short) | Area | Type | AI/Non-AI | Risk | SP | Status | Start Date | Completed Date | Dependencies | Acceptance Criteria Ref | Tracker Notes (Dev Agent)
1 | Workspace & Foundation | 1.1 | Wire Teacher app into workspace & gateway routing | Workspace: Teacher frontend/backend wired into monorepo + gateway | Workspace / Gateway | Hardening | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | None | Backlog § Task 1.1 Checklist | RBAC updated for Teacher+Admin; gateway proxy maps /api/teacher → :3003
1 | Workspace & Foundation | 1.2 | Teacher backend skeleton (NestJS service) | Backend: Teacher NestJS service skeleton with core modules | Teacher Backend | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 1.1 | Backlog § Task 1.2 Checklist | Full NestJS skeleton: 7 modules + guards + filters + interceptors + Swagger + seeder
1 | Workspace & Foundation | 1.3 | Teacher DB schema & migrations (core tables) | Data: core Teacher tables migrated (class, sessions, tests, etc.) | Teacher Backend — Data | Hardening | Non-AI | Low | 3 | Done | 2026-03-02 | 2026-03-02 | 1.2 | Backlog § Task 1.3 Checklist | 12 entities + 6 repositories + dev seeder with test data (UID sync ready)
1 | Workspace & Foundation | 1.4 | Shared contracts for Teacher APIs in @mindforge/shared | Shared: Teacher DTOs/enums in @mindforge/shared | Shared | Feature | Non-AI | Low | 1 | Done | 2026-03-02 | 2026-03-02 | 1.2 | Backlog § Task 1.4 Checklist | 14 interfaces + 8 enums in shared/src/interfaces/teacher/
2 | Class & Attendance Backend | 2.1 | Class & timetable domain (class, sessions, mappings) | Backend: classes, sessions, student mappings for attendance | Teacher Backend — Class & Attendance | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 1.3 | Backlog § Task 2.1 Checklist | 9 CRUD endpoints: classes + sessions + student mappings via ClassController + ClassService
2 | Class & Attendance Backend | 2.2 | Attendance mark entry APIs (per class session) | Backend: mark attendance per session with default Present | Teacher Backend — Class & Attendance | Feature | Non-AI | Low | 3 | Done | 2026-03-02 | 2026-03-02 | 2.1 | Backlog § Task 2.2 Checklist | Default-Present pattern; mark absentees only; same-day edit window via editable_until
2 | Class & Attendance Backend | 2.3 | Attendance aggregation & weekly absence alerts job | Backend: aggregate attendance + >2 days/week absence alerts | Teacher Backend — Analytics/Notifications | Feature | Non-AI | Medium | 3 | Done | 2026-03-02 | 2026-03-02 | 2.2 | Backlog § Task 2.3 Checklist | Daily/weekly/monthly summaries + >2 days/week absence → notification_event alerts
3 | Syllabus & AI Ingestion | 3.1 | Syllabus upload API & storage | Backend: upload syllabus files to storage + metadata | Teacher Backend — Syllabus | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 1.3 | Backlog § Task 3.1 Checklist | Multipart upload + file validation (type/MIME/size) + local FS storage + retry-failed endpoint
3 | Syllabus & AI Ingestion | 3.2 | AI ingestion worker: OCR + concept extraction → lesson_session | AI: OCR + LLM to create lesson_session from syllabus | Teacher Backend — AI Orchestration | Feature | AI | Medium | 3 | Done | 2026-03-02 | 2026-03-02 | 3.1 | Backlog § Task 3.2 Checklist | PDF parse + OpenAI chat completions + fallback analysis + lesson_session creation + status tracking
3 | Syllabus & AI Ingestion | 3.3 | Syllabus & lesson read APIs for frontend | Backend: list uploads, concepts, objectives, flags for UI | Teacher Backend — Syllabus | Feature | Non-AI | Low | 3 | Done | 2026-03-02 | 2026-03-02 | 3.2 | Backlog § Task 3.3 Checklist | 5 read endpoints: doc list/detail + lesson list/detail/by-document with JSON array parsing
4 | Tests & Evaluation Backend | 4.1 | Test domain & authoring APIs (online + offline) | Backend: test_definition authoring for quizzes & offline tests | Teacher Backend — Tests | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 3.3 | Backlog § Task 4.1 Checklist | 6 endpoints: CRUD + publish + close; online enforces MCQ/FIB/T-F only
4 | Tests & Evaluation Backend | 4.2 | Online daily quiz AI question generation (no numericals) | AI: generate objective-only quiz questions with no numericals | Teacher Backend — AI Orchestration | Feature | AI | Medium | 3 | Done | 2026-03-02 | 2026-03-02 | 4.1, 3.2 | Backlog § Task 4.2 Checklist | AI pipeline + prompt-level + code-level no-numerical enforcement + fallback
4 | Tests & Evaluation Backend | 4.3 | Offline printable test generation & PDF export | AI: offline tests with PDFs for student paper & answer key | Teacher Backend — Tests | Feature | AI | Medium | 3 | Done | 2026-03-02 | 2026-03-02 | 4.1, 3.2 | Backlog § Task 4.3 Checklist | All 7 question types + numerical stepwise solutions + Student Paper/Answer Key
4 | Tests & Evaluation Backend | 4.4 | Evaluation APIs (online auto-grade + offline mark entry) | Backend: auto-grade online + flows for offline marks | Teacher Backend — Evaluation | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 4.1, 4.2, 4.3 | Backlog § Task 4.4 Checklist | 7 endpoints: auto-grade + auto-submit + offline marks + per-student results
5 | Analytics & Notifications | 5.1 | Teacher analytics data APIs (performance & attendance) | Backend: KPIs and trends for Results & Analytics | Teacher Backend — Analytics | Feature | Non-AI | Low | 3 | Done | 2026-03-02 | 2026-03-02 | 2.3, 4.4 | Backlog § Task 5.1 Checklist | Class KPIs + score trends + attendance trends + at-risk detection (<75% attend / <40% score)
5 | Analytics & Notifications | 5.2 | Notifications & alerts pipeline (teacher-facing) | Backend: absence + test-related alerts for teacher | Teacher Backend — Notifications | Feature | Non-AI | Medium | 3 | Done | 2026-03-02 | 2026-03-02 | 2.3, 4.4 | Backlog § Task 5.2 Checklist | 5 endpoints: list + unread count + mark read + test alerts (auto-submit + eval pending)
5 | Analytics & Notifications | 5.3 | Cross-app read APIs for Student/Parent/Admin | Backend: Teacher aggregates exposed for other apps | Teacher Backend — Integration | Feature | Non-AI | Medium | 2 | Done | 2026-03-02 | 2026-03-02 | 5.1 | Backlog § Task 5.3 Checklist | 4 read-only endpoints: attendance summary + student attendance + performance + student test results
6 | Teacher Frontend — Core | 6.1 | Teacher frontend app shell, routing & auth | Frontend: app shell + sidebar nav + auth for Teacher | Teacher Frontend | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 1.1, 1.4 | Backlog § Task 6.1 Checklist | React 19+Vite shell; 8 routes; JWT auth context; bottom nav (5 tabs); API client w/ retry+upload; design tokens
6 | Teacher Frontend — Core | 6.2 | Dashboard screen (teacher overview) | Frontend: Dashboard with today's classes, KPIs, alerts | Teacher Frontend | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 6.1, 5.1, 5.2 | Backlog § Task 6.2 Checklist | Greeting + 2x2 KPI grid + today's classes + recent alerts + bell icon + loading/error/empty states
6 | Teacher Frontend — Core | 6.3 | Classes & Attendance screen (desktop + mobile) | Frontend: take attendance per session, default Present | Teacher Frontend | Feature | Non-AI | Low | 3 | Done | 2026-03-02 | 2026-03-02 | 6.1, 2.2 | Backlog § Task 6.3 Checklist | Class pills + session list + P/A toggle pills (48px) + summary chips + sticky save footer
6 | Teacher Frontend — Core | 6.4 | Attendance calendar & summaries on frontend | Frontend: calendar and summary views for attendance | Teacher Frontend | Feature | Non-AI | Low | 1 | Done | 2026-03-02 | 2026-03-02 | 6.3, 2.3 | Backlog § Task 6.4 Checklist | Monthly calendar grid + present/absent dots + summary stats + student breakdown table
7 | Teacher Frontend — Content & Assessments | 7.1 | Syllabus upload & concepts UI | Frontend: Syllabus screen with uploads + AI concepts | Teacher Frontend — Syllabus | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 6.1, 3.3 | Backlog § Task 7.1 Checklist | Upload zone + status badges (4 states) + lesson detail (concepts/objectives/chapters) + retry
7 | Teacher Frontend — Content & Assessments | 7.2 | Tests UI (online daily quiz + offline printable) | Frontend: Tests screen for quizzes + printable tests | Teacher Frontend — Tests | Feature | AI | Medium | 3 | Done | 2026-03-02 | 2026-03-02 | 6.1, 4.2, 4.3 | Backlog § Task 7.2 Checklist | Online/Offline tabs + create forms + AI generation + PDF download + lifecycle (draft/publish/close)
7 | Teacher Frontend — Content & Assessments | 7.3 | Results & Analytics UI | Frontend: Results & Analytics dashboards | Teacher Frontend — Analytics | Feature | Non-AI | Low | 2 | Done | 2026-03-02 | 2026-03-02 | 6.1, 5.1 | Backlog § Task 7.3 Checklist | Class KPIs + score bar chart + attendance weekly bars + at-risk students table
7 | Teacher Frontend — Content & Assessments | 7.4 | Alerts / Messages UI | Frontend: Alerts/Messages listing teacher notifications | Teacher Frontend — Notifications | Feature | Non-AI | Low | 1 | Done | 2026-03-02 | 2026-03-02 | 6.1, 5.2 | Backlog § Task 7.4 Checklist | Filter tabs + priority borders + read/unread tracking + mark all read + unread badge
8 | Hardening & AI Guardrails | 8.1 | Teacher service observability (logs, metrics, tracing) | DevOps: observability for Teacher backend | DevOps / Teacher Backend | Hardening | Non-AI | Low | 2 | Done | 2026-02-10 | 2026-02-10 | 1.2 | Backlog § Task 8.1 Checklist | MetricsService + liveness/readiness probes + structured JSON logging + startup diagnostics
8 | Hardening & AI Guardrails | 8.2 | AI governance & guardrails (teacher domain) | AI: guardrails, rate limits, logging for Teacher AI | Teacher Backend — AI Governance | Hardening | AI | Medium | 3 | Done | 2026-02-10 | 2026-02-10 | 3.2, 4.2, 4.3 | Backlog § Task 8.2 Checklist | AiAuditService (no PII) + AiRateLimiterService (20/teacher/hr + 200 global/hr) + NumericalValidatorService (14 patterns)
8 | Hardening & AI Guardrails | 8.3 | Performance and load validation for Teacher flows | Perf: load validation for key Teacher flows | Performance | Hardening | Non-AI | Low | 2 | Done | 2026-02-10 | 2026-02-10 | 2.x–7.x | Backlog § Task 8.3 Checklist | PerformanceInterceptor (slow-request logging) + performance budgets for 5 critical flows
8 | Hardening & AI Guardrails | 8.4 | Cross-app integration validation (Student/Parent/Admin) | Integration: validate Teacher APIs for other apps | Integration | Hardening | Non-AI | Medium | 1 | Done | 2026-02-10 | 2026-02-10 | 5.3 | Backlog § Task 8.4 Checklist | IntegrationHealthController + @CrossAppEndpoint decorator + cross-app logging + RBAC validation

## Sprint Summary
Sprint # | Sprint Name | Capacity (SP) | Planned SP | Tasks | Done | Remaining
1 | Workspace & Foundation | 10 | 8 | 4 | 4 | 0
2 | Class & Attendance Backend | 10 | 8 | 3 | 3 | 0
3 | Syllabus & AI Ingestion | 10 | 8 | 3 | 3 | 0
4 | Tests & Evaluation Backend | 10 | 10 | 4 | 4 | 0
5 | Analytics & Notifications | 10 | 8 | 3 | 3 | 0
6 | Teacher Frontend — Core | 10 | 8 | 4 | 4 | 0
7 | Teacher Frontend — Content & Assessments | 10 | 8 | 4 | 4 | 0
8 | Hardening & AI Guardrails | 10 | 8 | 4 | 4 | 0
Category | Count
Done | 29
Remaining | 0