## Project Tracking
Sprint # | Sprint Name | Task ID | Task Title | User Story (short) | Area | Type | AI/Non-AI | Risk | SP | Status | Start Date | Completed Date | Dependencies | Acceptance Criteria Ref | Tracker Notes (Dev Agent)
1 | Foundation & Auth | 1.1 | API gateway and request validation | Backend: REST gateway, validation, consistent error shape | Backend — API | Hardening | Non-AI | Low | 2 | Done | 2026-02-10 | 2026-02-11 | None | Backlog § Task 1.1 Checklist | REBUILT on NestJS+TypeScript (locked stack). Modular: /modules/{auth,student,attendance,activities} with controller/service/repository/policy pattern. Global: Helmet headers; HTTPS enforce; CORS; JSON-only; class-validator DTO pipes (whitelist+forbidNonWhitelisted); GlobalExceptionFilter → {code,message,details?} for 400-500; RequestId interceptor; LoggingInterceptor; ThrottlerGuard (X-RateLimit headers); AuthGuard (@Public bypass); AuthorizationGuard; AuditService. Health: GET /health. Auth: POST /v1/auth/mpin/verify¦lockout/status¦forgot-mpin with DTO validation → service stubs. OpenAPI/Swagger at /api/docs. Zero TS build errors.
1 | Foundation & Auth | 1.2 | MPIN verify and token/session issuance | Student: enter 6-digit MPIN, get token/session | Backend — Auth | Feature | Non-AI | Medium | 3 | Done | 2026-02-11 | 2026-02-11 | 1.1 | Backlog § Task 1.2 Checklist | POST /v1/auth/mpin/verify: bcrypt MPIN hash verification via AuthRepository (in-memory store with seeded test student; DB in Task 2.1). On success: JWT issued (sub=studentId, 1h expiry, issuer=mindforge-backend) via @nestjs/jwt; session recorded. On failure: 401 INVALID_CREDENTIALS (generic msg — no identity leak). Lockout: AuthPolicy enforces 5 attempts → 15 min lockout (403 ACCOUNT_LOCKED with lockedUntil). Rate limit: @Throttle 10 req/60s on mpin/verify. Audit: LOGIN_SUCCESS/LOGIN_FAILURE/LOGIN_BLOCKED_LOCKOUT via AuditService (requestId+IP+studentId). No MPIN in logs or response. lockout/status endpoint returns live lockout state.
1 | Foundation & Auth | 1.3 | Lockout status and Forgot MPIN entry points | Student: see lockout status and Forgot MPIN path | Backend — Auth | Feature | Non-AI | Low | 2 | Done | 2026-02-11 | 2026-02-11 | 1.2 | Backlog § Task 1.3 Checklist | POST /v1/auth/lockout/status: fully implemented — returns isLocked, lockedUntil, attemptsRemaining, maxAttempts (5), lockoutDurationMinutes (15). Unknown studentId returns generic not-locked (no identity leak). DTO validates studentId as UUID; 400 on invalid. POST /v1/auth/forgot-mpin: returns 202 Accepted with documented message — v1 entry point only; full OTP flow deferred. Audit: FORGOT_MPIN_INITIATED logged. Error shape consistent: {code,message,details?} on all error paths.
1 | Foundation & Auth | 1.4 | Auth middleware and Bearer token validation | Backend: validate Bearer on protected routes | Backend — API | Hardening | Non-AI | Low | 1 | Done | 2026-02-11 | 2026-02-11 | 1.2 | Backlog § Task 1.4 Checklist | AuthGuard now verifies JWT via JwtService.verifyAsync with ConfigService secret. Expired token → 401 TOKEN_EXPIRED; invalid/wrong-secret → 401 INVALID_TOKEN; missing header → 401 UNAUTHORIZED. On success: extracts sub/studentId/class/board from JWT payload and attaches to request.student. @Student() param decorator for clean controller access. @Public() routes bypass guard. AuthModule @Global() exports JwtModule for guard DI. GET /v1/student/me added as protected endpoint demo — returns authenticated student context. No cross-student access: business layer scoped to request.student.id.
2 | Data & Backend Core | 2.1 | Database schema and migrations | System: versioned schema for students, activities, etc. | Backend — Data | Hardening | Non-AI | Low | 3 | Done | 2026-02-12 | 2026-02-12 | None | Backlog § Task 2.1 Checklist | TypeORM + PostgreSQL (prod) / better-sqlite3 (dev). 11 entities: students, syllabus_metadata, teaching_feed, activities, questions, responses, attendance, doubt_threads, doubt_messages, sessions, audit_log. Indexes: student_id, activity_id, date (attendance), syllabus composite (class+board+subject+chapter). Versioned migration: InitialSchema20260211001 with up/down (idempotent). DatabaseModule configures TypeORM via ConfigService; synchronize in dev, migrations in prod. All per Architecture §5.1.
2 | Data & Backend Core | 2.2 | Data access layer (repositories/DAOs) | Business layer: repositories for all entities | Backend — Data | Feature | Non-AI | Low | 3 | Done | 2026-02-12 | 2026-02-12 | 2.1 | Backlog § Task 2.2 Checklist | 10 repositories: StudentRepo, SyllabusRepo, TeachingFeedRepo, ActivityRepo, QuestionRepo, ResponseRepo, AttendanceRepo, DoubtRepo, SessionRepo, AuditLogRepo. BaseRepository with withErrorHandling(): transient DB errors (deadlock, connection) → retry 3x with exponential backoff; unique constraint → 409 ConflictException; all queries parameterized via TypeORM. All queries scoped by student_id. AuthRepository migrated to TypeORM (students+sessions from DB, lockout in-memory until Redis). AuditService now persists to audit_log table.
2 | Data & Backend Core | 2.3 | Business layer skeleton and dependency injection | API layer: business logic calls data access only | Backend — Business | Hardening | Non-AI | Low | 2 | Done | 2026-02-12 | 2026-02-12 | 2.2 | Backlog § Task 2.3 Checklist | Business services: StudentService (today's plan, profile, sync status), ActivitiesService (get activity, submit answer, pause, results), GradingService (deterministic MCQ/TF/fill-blank; AI stub for open-ended), AttendanceService (summary+calendar), DoubtService (threads, messages, AI stub). Domain exceptions: InvalidMpinException, AccountLockedException, ActivityNotFoundException, ActivityAlreadyCompletedException, QuestionNotFoundException, DoubtThreadNotFoundException, StudentNotFoundException, AiUnavailableException — all mapped to HTTP codes. API→Service→Repo layering enforced.
3 | Today's Plan & Activities API | 3.1 | GET /student/today (today's plan) | Student: get today's tasks and progress summary | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-13 | 2026-02-13 | 2.2, 2.3 | Backlog § Task 3.1 Checklist | GET /v1/student/today: returns student context (id, displayName, class, board) + task cards (id, type, title, syllabusRef{subject,chapter,topic}, questionCount, estimatedMinutes, status, score) + completedToday/totalToday/progressPercent. Auth required; scoped by student_id via @Student() decorator. Empty state: empty tasks array with 0 progress. GET /v1/student/profile: returns profile + totalActivitiesCompleted. DevSeederService seeds 3 activities + 5 questions + 10 attendance records in dev. Coding standards applied: no TODOs, explicit edge cases, domain exceptions only.
3 | Today's Plan & Activities API | 3.2 | GET /student/activities/:type/:id and POST pause | Student: open activity, see questions, pause/save progress | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-13 | 2026-02-13 | 2.2, 2.3 | Backlog § Task 3.2 Checklist | GET /v1/student/activities/:type/:id: returns activity metadata + questions (id, type, content, options, difficulty, sortOrder, answered). Correct answers never exposed. PENDING→IN_PROGRESS on first access. Types: homework, quiz, test, gap_bridge. 404 if not found or not assigned. POST /v1/student/activities/:type/:id/pause: saves progress, marks PAUSED. No-op if already completed. Auth required; scoped by student_id.
3 | Today's Plan & Activities API | 3.3 | POST /student/activities/:type/:id/respond | Student: submit answer, get correct/incorrect (deterministic grading) | Backend — Business | Feature | Non-AI | Low | 3 | Done | 2026-02-13 | 2026-02-13 | 3.2 | Backlog § Task 3.3 Checklist | POST /v1/student/activities/:type/:id/respond: accepts {questionId, answer, requestFeedbackLevel?}. DTO validation: UUID for questionId, non-empty answer, optional FeedbackLevel enum. Deterministic grading for MCQ/TRUE_FALSE/FILL_BLANK (case-insensitive compare). Returns {questionId, isCorrect, score, feedback, feedbackLevel, isComplete, nextQuestionId}. Idempotent: duplicate submit returns existing result. Auto-completes activity when all questions answered (updates status+score). 409 if activity already completed. 404 for unknown activity/question.
3 | Today's Plan & Activities API | 3.4 | GET /student/results/:type/:id | Student: get activity result (score, breakdown, suggested next) | Backend — Business | Feature | Non-AI | Low | 1 | Done | 2026-02-13 | 2026-02-13 | 3.3 | Backlog § Task 3.4 Checklist | GET /v1/student/results/:type/:id: returns activityId, type, title, status, totalQuestions, answeredQuestions, correctAnswers, score (0-100), per-question breakdown [{questionId, isCorrect, score}], suggestedNext [{type, title, reason}]. Suggested next based on performance: <60%→gap_bridge, 60-89%→quiz, 90%+→next topic. Auth required; scoped by student_id. 404 if not found.
4 | AI Integration & Grading | 4.1 | AI provider integration and timeout/fallback | Business layer: call AI with timeout and fallback | Backend — Integration | Feature | AI | Medium | 3 | Done | 2026-02-16 | 2026-02-16 | 2.3 | Backlog § Task 4.1 Checklist | AiProviderService: OpenAI-compatible HTTP client using native fetch+AbortController. 10s timeout → deterministic fallback. Response validated (sanitized, no raw errors). Token usage logged (model, tier, tokens, latency). FallbackConfig per call site. PromptBuilderService: typed prompt builders for grading, feedback, doubt — all use syllabus context only (no PII, pseudonymous). Cost tiering: grading=cheap model, feedback=higher model. Config: AI_BASE_URL, AI_API_KEY, AI_GRADING_MODEL, AI_FEEDBACK_MODEL, AI_TIMEOUT_MS, AI_MAX_TOKENS, AI_TEMPERATURE. AiModule @Global.
4 | AI Integration & Grading | 4.2 | GET /student/activities/:type/:id/feedback (progressive guidance) | Student: next AI guidance level (Hint → Approach → Concept → Solution) | Backend — Business | Feature | AI | Medium | 3 | Done | 2026-02-16 | 2026-02-16 | 3.3, 4.1 | Backlog § Task 4.2 Checklist | GET /v1/student/activities/:type/:id/feedback?questionId=&level=. FeedbackService enforces level order: Hint→Approach→Concept→Solution. Auto-advances if no level specified. No skipping (resolveTargetLevel ensures monotonic progression). Returns {questionId, level, content, fromAi, nextLevel, maxLevelReached}. Persists feedbackLevel+aiFeedback+aiConversationRef to response entity. Fallback: static syllabus-aware hints when AI unavailable. 404 for unknown activity/question.
4 | AI Integration & Grading | 4.3 | Deterministic and AI-assisted grading rules | System: deterministic for objective; AI/rubric for open-ended | Backend — Business | Feature | AI | Low | 2 | Done | 2026-02-16 | 2026-02-16 | 3.3, 4.1 | Backlog § Task 4.3 Checklist | GradingService: MCQ/TRUE_FALSE/FILL_BLANK → deterministic (case-insensitive exact match, score 0/100). SHORT_ANSWER/LONG_ANSWER → AI-assisted via AiProviderService with rubric context; parseGradingResponse extracts JSON {isCorrect, score, feedback}; score clamped 0-100. No API key → graceful 'pending' status. ActivitiesService.submitAnswer now delegates to GradingService. AI grading results stored: aiFeedback+aiConversationRef in response entity. No PII in prompts.
5 | Attendance & Doubts API | 5.1 | GET /student/attendance (summary and calendar) | Student: attendance summary and calendar for period | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-17 | 2026-02-17 | 2.2, 2.3 | Backlog § Task 5.1 Checklist | GET /v1/student/attendance: AttendanceController with AttendanceQueryDto — period shortcuts (this_month, last_month, this_term) or explicit startDate/endDate. Returns {summary: {studentId, period, totalDays, present, absent, late, attendancePercent}, calendar: [{date, status}]}. Default: this_month. Timezone-safe date formatting (no UTC shift). Auth required; scoped by student_id. Validation: enum for period, regex for YYYY-MM-DD. Empty state: 0 counts + empty calendar.
5 | Attendance & Doubts API | 5.2 | Doubts: GET list GET thread POST message with syllabus context | Student: doubt threads with Class→Subject→Chapter→Topic context | Backend — Business | Feature | AI | Medium | 3 | Done | 2026-02-17 | 2026-02-17 | 4.1, 2.2, 2.3 | Backlog § Task 5.2 Checklist | DoubtsController: GET /v1/student/doubts (list threads), GET /v1/student/doubts/:threadId (thread + messages), POST /v1/student/doubts (new thread or reply with syllabus context). DTO: CreateDoubtDto with message, optional threadId, syllabusClass/Subject/Chapter/Topic. Replies inherit thread's syllabus context. AI responses via AiProviderService with syllabus-aligned prompt (fallback on AI failure). GET /v1/student/syllabus/tree: SyllabusController+SyllabusService — returns Class→Subject→Chapter→Topic hierarchy from flat records. Both new modules registered.
5 | Attendance & Doubts API | 5.3 | GET /student/profile and GET /student/sync/status | Student: profile and sync status (conflict hint) | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-17 | 2026-02-17 | 2.2, 2.3 | Backlog § Task 5.3 Checklist | Enhanced profile: GET /v1/student/profile now returns progressOverview [{type, total, completed, averageScore}] via ActivityRepository.getProgressOverviewForStudent (GROUP BY type, AVG score). GET /v1/student/sync/status: returns {lastSyncAt, hasConflict, conflictHint?}. Stub — real sync tracking deferred to Sprint 7. Auth required; scoped by student_id.
6 | Client — Login Home Activity Results | 6.1 | Client app shell and API client (auth REST error shape) | Client: Bearer token, error shape, retry | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-18 | 2026-02-18 | API contract | Backlog § Task 6.1 Checklist | React+TS+Vite scaffolded in /client. API client (src/api/client.ts): base URL, Bearer auth, JSON parse, {code,message,details?} error shape, AbortController timeout (15s), 2x retry on network errors, offline detection. AuthContext: login/logout, sessionStorage token persistence. Vite proxy /v1→localhost:3000. Design tokens (theme.css): sage green, deep brown, cream per UX. BottomNav + Skeleton components. Zero TS errors; 80KB gzipped.
6 | Client — Login Home Activity Results | 6.2 | Login screen (Screen 1) per UX spec | Student: 6-digit MPIN, keypad, error/lockout states | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 1.2, 1.3 | Backlog § Task 6.2 Checklist | Route /login. 6-digit MPIN dots + on-screen keypad. Auto-submit on 6th digit. States: default, entering, loading (spinner), error (red border + message + attempts remaining), locked (countdown timer). Forgot MPIN link. Accessibility: aria-label on keypad, role=alert for errors. Navigate to /home on success.
6 | Client — Login Home Activity Results | 6.3 | Home screen (Screen 2) — Today's Plan | Student: task cards, progress bar, completed today | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 3.1 | Backlog § Task 6.3 Checklist | Route /home. Greeting (time-based), student name. Progress bar (percent + X of Y). Task cards: type badge, status badge, title, subject, question count, estimated time, score. States: loading (skeleton), default, empty (All caught up!), error (Try Again). Tap card → /activity/:type/:id or /results/:type/:id. BottomNav: Home, Attendance, Doubts, Profile.
6 | Client — Login Home Activity Results | 6.4 | Activity screen (Screen 3) — question answer AI feedback panel | Student: question, submit answer, AI feedback or fallback | Frontend | Feature | AI | Medium | 3 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 3.2, 3.3, 4.2 | Backlog § Task 6.4 Checklist | Route /activity/:type/:id. Question flow: progress bar, MCQ options or text input, Check Answer. Submitting → correct (green) or incorrect (red + AI feedback panel). Feedback panel: Get a Hint → More Help (progressive levels). AI thinking indicator. Pause/exit saves progress. Auto-advances to next unanswered question. Complete state → View Results. Accessibility: question labelled, progress aria-label.
6 | Client — Login Home Activity Results | 6.5 | Results screen (Screen 4) | Student: score, breakdown, suggested next | Frontend | Feature | Non-AI | Low | 1 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 3.4 | Backlog § Task 6.5 Checklist | Route /results/:type/:id. Score circle (gradient), star rating (1-5), per-question breakdown (✓/✗ with scores), Suggested Next cards (type + title + reason), Back to Home. States: loading (skeleton), success, perfect score celebration (🎉). 256KB JS bundle.
7 | Client — Attendance Doubts Profile & Sync | 7.1 | Attendance screen (Screen 5) — calendar and summary | Student: attendance summary and calendar | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-19 | 2026-02-19 | 6.1; API 5.1 | Backlog § Task 7.1 Checklist | Route /attendance. Period selector (This Month/Last Month/This Term). Summary card: Present, Absent, Late, Rate. Calendar grid (7-col, day numbers in coloured dots). Legend. States: loading (skeleton), default, empty, error (retry). Uses GET /v1/student/attendance?period=. Timezone-safe date formatting. Fully responsive 480px max-width.
7 | Client — Attendance Doubts Profile & Sync | 7.2 | Doubts screen (Screen 6) with syllabus context selector | Student: AI chat with Class→Subject→Chapter→Topic context | Frontend | Feature | AI | Medium | 3 | Done | 2026-02-19 | 2026-02-19 | 6.1; API 5.2 | Backlog § Task 7.2 Checklist | Route /doubts. Thread list + chat view. Syllabus context bar (Subject·Chapter·Topic) with Change picker (cascading dropdowns from GET /v1/student/syllabus/tree). Chat: student/AI bubbles, auto-scroll, thinking indicator, Enter-to-send. Ask a Doubt creates new thread; replies inherit context. States: loading, empty, error. SendIcon SVG.
7 | Client — Attendance Doubts Profile & Sync | 7.3 | Profile screen and logout | Student: profile (name, class, board, progress) and logout | Frontend | Feature | Non-AI | Low | 1 | Done | 2026-02-19 | 2026-02-19 | 6.1; API 5.3 | Backlog § Task 7.3 Checklist | Route /profile. Avatar initial, name, Class/Board chips, school. Progress Overview: per-type mini progress bar (completed/total + avg score). Quick Links to Attendance and Doubts. Logout with confirmation dialog. Uses GET /v1/student/profile. Clears sessionStorage on logout → /login.
7 | Client — Attendance Doubts Profile & Sync | 7.4 | Sync status and conflict modal | Student: sync status; conflict Use latest? / Keep current | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-19 | 2026-02-19 | 6.1, 6.3; API 5.3 | Backlog § Task 7.4 Checklist | SyncBanner component on HomeScreen. Polls GET /v1/student/sync/status every 60s. Green dot + 'All caught up!' when synced. Orange dot + conflict modal on hasConflict=true: 'Found newer progress on another device' with [Keep Current] [Use Latest] actions. Overlay with stopPropagation. Fully typed SyncStatus interface.
8 | Teacher-Grounded AI Integration & DevOps | 8.1 | Teacher upload API and file storage integration | Teacher: upload PDF/notes via API with file validation | Backend — Activities Module | Feature | Non-AI | Medium | 2 | Done | 2026-02-20 | 2026-02-20 | 2.1, 2.2, 2.3 | Backlog § Task 8.1 Checklist | TeacherContentController: POST /v1/teacher/materials/upload (multipart) + GET /v1/teacher/materials + POST /:id/retry. File validation (PDF/DOCX/TXT 20MB MIME+ext). Local storage in dev. teacher_materials entity+repo. X-Teacher-Id header. Audit logging.
8 | Teacher-Grounded AI Integration & DevOps | 8.2 | PDF parsing and chunking pipeline | System: parse PDFs/docs into text and split into semantic chunks | Backend — Activities Module | Feature | AI | Medium | 2 | Done | 2026-02-20 | 2026-02-20 | 8.1 | Backlog § Task 8.2 Checklist | TeacherContentService.processAsync: pdf-parse v1 for PDF extraction. Text cleaning (headers/footers/page numbers). Semantic chunking ~500 tokens with ~50 token overlap preserving paragraph boundaries. teacher_material_chunks entity. Async non-blocking. Failure → status=failed.
8 | Teacher-Grounded AI Integration & DevOps | 8.3 | Embedding generation and vector storage | System: generate vector embeddings for chunks; store in pgvector | Backend — Activities Module | Feature | AI | Medium | 2 | Done | 2026-02-20 | 2026-02-20 | 8.2 | Backlog § Task 8.3 Checklist | Embedding via OpenAI text-embedding-3-small (configurable). Batch 20 chunks/call. JSON text in SQLite dev (pgvector for prod). EmbeddingsRepository with cosine similarity search in-memory. On failure: status=failed. HNSW/IVFFlat index path for PostgreSQL.
8 | Teacher-Grounded AI Integration & DevOps | 8.4 | Retrieval service (vector search integration) | Activities: search teacher material by semantic similarity | Backend — Activities Module | Feature | AI | Medium | 1 | Done | 2026-02-20 | 2026-02-20 | 8.3 | Backlog § Task 8.4 Checklist | RetrievalService: embeds student question via same model. Vector similarity search scoped by class/subject. Top-K=5 configurable. Confidence threshold=0.7 configurable. Below threshold → empty → 'Not found in provided material.' 10s timeout.
8 | Teacher-Grounded AI Integration & DevOps | 8.5 | AI retrieval orchestration service | Activities: build retrieval-augmented prompts; call AI with strict grounding | Backend — Activities Module | Feature | AI | Medium | 1 | Done | 2026-02-20 | 2026-02-20 | 4.1, 8.4 | Backlog § Task 8.5 Checklist | AiOrchestratorService: system prompt enforcing retrieval-only answering + [chunk:{id}] citation. Retrieved chunks as sole context. Temperature 0.15. On timeout/error: fail closed → 'Not found in provided material.' Conversation history (last 6 msgs).
8 | Teacher-Grounded AI Integration & DevOps | 8.6 | Strict response validator service | System: validate AI responses for citations and on-topic alignment | Backend — Activities Module | Feature | AI | Low | 1 | Done | 2026-02-20 | 2026-02-20 | 8.5 | Backlog § Task 8.6 Checklist | ResponseValidatorService: regex [chunk:{uuid}] citation extraction. Validates cited IDs in retrieved set. Rejects no-citation responses. Heuristic off-topic markers ('based on my training' etc). Returns validated response + cited_chunk_ids or fail closed.
8 | Teacher-Grounded AI Integration & DevOps | 8.7 | AI usage logging and monitoring | System: log AI usage (tokens, latency, retrieval stats); monitor cost/quality | Backend — Activities Module / DevOps | Feature | Non-AI | Low | 1 | Done | 2026-02-20 | 2026-02-20 | 8.5, 8.6, 2.1 | Backlog § Task 8.7 Checklist | ai_usage_logs entity: student_id feature_type model tokens latency retrieval_stats response_status rejection_reason. AiUsageRepository aggregations. AiUsageLoggerService non-blocking wrapper. All AI calls (doubt pipeline) log usage.
8 | Teacher-Grounded AI Integration & DevOps | 8.8 | Security: file validation and access control and audit | System: strict file validation; access control for material retrieval; audit | Backend — Security | Hardening | Non-AI | Medium | 1 | Done | 2026-02-20 | 2026-02-20 | 8.1, 8.4 | Backlog § Task 8.8 Checklist | File validation: MIME+extension whitelist 20MB. X-Teacher-Id access control. Student retrieval scoped by class at repo level. No raw material to students. Audit log upload/retry. Rate limiting via ThrottlerGuard. Multipart through JsonOnlyMiddleware.
8 | Teacher-Grounded AI Integration & DevOps | 8.9 | DevOps: storage bucket and embedding worker and deployment and monitoring | Team: cloud storage; async embedding worker; CI/CD; monitoring | DevOps | Hardening | Non-AI | Low | 2 | Done | 2026-02-20 | 2026-02-20 | 8.1, 8.2, 8.3 | Backlog § Task 8.9 Checklist | TEACHER_STORAGE_PATH EMBEDDING_MODEL RETRIEVAL_CONFIDENCE_THRESHOLD RETRIEVAL_TOP_K env vars. Async in-process worker. NestJS build clean. New entities auto-migrate dev. CORS X-Teacher-Id. Production: S3/GCS storage pgvector embedding worker documented.
Chart Data
Status | Count
Completed | 35
Remaining | 0
Sprint | Done | Remaining | Story Points
S1 | 4 | 0 | 8
S2 | 3 | 0 | 8
S3 | 4 | 0 | 8
S4 | 3 | 0 | 8
S5 | 3 | 0 | 7
S6 | 5 | 0 | 10
S7 | 4 | 0 | 8
S8 | 9 | 0 | 13